BUSINESS PLAN

Gold Coast

Pride House International

2018

“Achieving Success”

Contents

Page 3:			Executive Summary

Page 4:			Vision

Page 4:			Mission

Page 4:			Values

Page 4:			Stakeholders

Page 5:			S.C.O.R.E. Analysis

Page 6:			Key Result Areas

Page 7:			Plan

Page 16:			Future

Page 17:			Appendix A (Budget)

Executive Summary

This Business Plan sets forth the Vision, Core Values, Key Results Areas, Outcomes, Strategies and timelines of the Pride House International Gold Coast 2018 for the 20017 – 2018 period.

This document is being developed after Community Collaboration and consultation of interested stakeholders. Input has been received through a number of means; however the majority of input has come via the following sources:

- Community Consultation 29 July 2017 The Arts Centre, Gold Coast

- Interested Stakeholders Meeting 10 September 2017 The Arts Centre, Gold Coast

- Pride House International Conversation and Update Meeting 2 November 2017 Gold Coast 2018 Commonwealth Games Corporation (GOLDOC) Headquarters

- Individual feedback

The Meetings have been attended by Stakeholders representing:

- GOLDOC

- Office of Commonwealth Games (State Government)

- The Star Casino

- The Arts Centre, Gold Coast

- Griffith University (Pride)

- Queensland Police Service

- LGBTI Legal Service (Brisbane)

- Pride in Sport/ACON

- Queensland AIDS Council

- Team Rainbow Incorporated

- Proud 2 Play

- Young Leaders Embracing 2018 (YLE18) Committee

- Gay and Lesbian International Sport Association (GLISA AUS & NZ)

- Pride House International

- Intersex representatives

- Transgender representatives

- First Nations representatives

- LGBTIQ Human Rights Activists

It is now time to ensure that all of our stakeholders receive the best possible opportunities and outcomes from a successful Gold Coast Pride House International 2018 Project.

Our Vision

To provide a safe and inclusive space for the LGBTIQ+ community during the Gold Coast 2018 Commonwealth Games to gather, celebrate and watch sport. To ensure the highest quality and most enjoyable experience is had by all Pride House International attendees and leaves a lasting legacy for the LGBTIQ+ sporting community on the Gold Coast.

Our Mission

- To educate and raise awareness of LGBTIQ+ People of the Commonwealth

- To facilitate best practice delivery of Gold Coast Pride House International (GCPHI) operations, to cater to stakeholder and LGBTIQ+ community needs

- To ensure the financial viability of GCPHI

- To positively influence and support all within LGBTIQ+ communities

- To provide opportunities for all stakeholders

- To help develop our volunteers

- To exceed our stakeholders’ expectations

- To form effective partnerships

- To achieve determined objectives.

Our Values

- We value safety

- We value inclusion for all

- We value equality

- We value a respectful environment in which all stakeholders can contribute

- We value fair, open, ethical and accountable behaviour

- We value best practice policies and procedures

- We value cooperation and operating as a team

Our Stakeholders

- Those highlighted on Page 3

- Ambassadors (Ji Wallace, Nat Cook, Matt Mitcham)

- Media; local, State, National, International (Traditional and Social)

- Organisations providing Funding

- State Government

- Gold Coast City Council

- Queensland Tourism

- Suppliers

- Venue

S.C.O.R.E. Analysis

| Strengths | Constraints |
| --- | --- |
| Supported by GOLDOC Previous Pride House’s International Staff input Volunteer’s enthusiasm & skills Stakeholders Surfers Paradise venue location (corner of Cavill Ave & The Esplanade) Public transport access Ambassadors Success of previous Pride House’s International Expectation of significant attendance Media interest, reach and exposure Financial management (Team Rainbow Inc.) Planned Exhibitions/Performances/Events | Lack of funding Planning, organisation, management of this Project is being done by volunteers GOLDOC |
| Opportunities | Risks |
| Significant GCPHI exposure Official Public Media Launch To raise LGBTIQ+ awareness and education To host 1 or 2 Exhibitions; The LGBTIQ+ People of the Commonwealth from PHI 2014 &/or an Australian LGBTIQ+ Sportspeople/Sporting History Exhibition To reduce Stigma and discrimination To provide free legal advice for those in need To host events promoting understanding on diverse topics Tourism Proactively work with GOLDOC to access their Sponsors and Partners Crowdfunding Request for a GOLDOC staff member be allocated some hours to assist with the delivery of the project Implement best practice structures, policies and procedures All volunteers to receive inclusiveness training (QuAC) Increased focus on servicing minority groups (i.e. First Nation peoples, Gender Diverse, culturally and linguistically diverse; people with a disability; others) Improved linkages with health promotion agencies (e.g. mental health, suicide prevention, Youth, First Nation peoples, Gender Diverse, others) Gender neutral bathrooms at Venue GCPHI2018 Launch Event/Opening Night (March 28 ) | Not receiving sufficient funding Risk Management Assessment The safety of those who identify as LGBTIQ+ outside of the venue GOLDOC support and assistance being reduced Lack of access to GOLDOC sponsors and partners Not meeting stakeholder expectations |
| Expectations (2017 – 2018) |
| Use this Plan to drive the Project Funding equal to Forecasting Budget Obtain ongoing support and assistance from GOLDOC and their partners Have a coordinated Project Management delivery and marketing approach Have best practice policies, procedures and systems in place across all areas of operation Have high levels of stakeholder satisfaction levels |

Key Result Areas

This Business Plan has been prepared to reflect the objectives, strategies, key dates/timeframes, roles and responsibilities of GCPHI2018.

From November 2017 - April 2018 we will focus on the following Key Result Areas –

| Key Result Area 1: Planning | Key Result Area 2: Communications, Marketing & Media |
| --- | --- |
| KRA 1: Planning Sub-Categories: Roles and Responsibilities, Project Management, Steering Committee Administration Risk Assessment Legacy | KRA 2: Communications, Marketing & Media Sub-Categories: Marketing / Media / Communications Strategy Media Launch (December) Traditional & Social Media Management and Reporting Project Opening (March 28) with Ambassadors on a panel |

| Key Result Area 3: Funding | Key Result Area 4: Operations |
| --- | --- |
| KRA 3: Funding Sub-Categories: Forecasting Budget Expenses Insurance Banking Revenue / Project Funding / Sponsorship / Grants | KRA 4: Operations Sub-Categories: Events Exhibitions Venue fit out Volunteers |

Our Plan

| KRA 1: Planning |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 1. Roles and Responsibilities | Project Management | - Establish required Team Leaders who are available to contribute a few hours weekly ie Marketing/Media, Ambassadors, Crowdfunding, Sponsorship, Events Program, Exhibitions | November |  |  |
|  | Steering Committee | - Continue regular meetings with collaborative input | Ongoing |  |  |
|  | GOLDOC | - Introductions to existing Sponsors - Media/Marketing assistance ie Launch | ? December |  |  |

| KRA 1: Planning |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 2. Administration | Information | - Regular email updates - MH requests assistance with Admin | Ongoing |  |  |
|  | Social Media Administrator | - Recommend John Tozeland (JWT Media) - Someone to assist John? | November |  |  |
|  | GOLDOC | - Designated Staff Member Assistance - Legal Support ie Contracts/MOU with Venue, Team Rainbow Inc. | November |  |  |

| KRA 1: Planning |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 3. Risk Assessment | Project Risk Assessment | - MH to complete | November |  |  |
|  | Venue Risk Assessment | - Venue to supply | November |  |  |
|  | GOLDOC Risk Assessment |  | ? |  |  |

| KRA 1: Planning |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 4. Legacy | What is the short term Legacy? | - Awareness & Education - Safety | Ongoing |  |  |
|  | Medium-Long term Legacy | - Inclusive & Equality projects - Established permanent outcomes ie GC Alliance Network, creation of an LGBTIQ+ Sporting Association | Ongoing |  |  |
|  | GOLDOC Legacy | – Engage LGBTIQ+ people around sport - Create pathways for GC LGBTIQ+ sport - Use GC2018 as a catalyst for a more LGBTIQ+ friendly & supportive mentality | Ongoing |  |  |

| KRA 2: Communications, Marketing & Media |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 1. Communications, Marketing & Media Strategy | Designated Comms, Marketing & Media Strategy | - Recommend John Tozeland and Ian Muchamore - Prepare Strategy for distribution | November December |  |  |
|  | Official Project Name & Logo | - GOLDOC to approve Name - Design/Circulate a few possible Logo’s | ASAP November |  |  |
|  | GOLDOC | - Marketing/Media Support & Assistance | Ongoing |  |  |

| KRA 2: Communications, Marketing & Media |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 2. Media Launch | Hold a Media Launch | - Ambassadors to be announced to the Public - Launch Funding/Sponsorship Proposal - Launch Crowd Funding | December December December |  |  |
|  | GOLDOC | - Request to be held at GOLDOC’s office - Media/Ambassador team to assist | December |  |  |

| KRA 2: Communications, Marketing & Media |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 3. Traditional/Social Media Management & Reporting | Traditional Media | - Regular editorials and interviews | Dec-April |  |  |
|  | Social Media | - Facebook, Twitter, Instagram | Dec-April |  |  |
|  | GOLDOC | - Support & Assistance | Ongoing |  |  |

| KRA 2: Communications, Marketing & Media |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 4. Pride House International Launch (March 28) | Official Opening of PHI | - Ambassadors on a Q & A panel - Invited Guests - Live Performers | March 28 | $3K |  |
|  | Exhibition/s unveiled | - Australian LGBTIQ Sportspeople - LGBTI People of the Commonwealth |  |  |  |
|  | GOLDOC | - Support & Assistance |  |  |  |

| KRA 3: Funding |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 1. Forecasting Budget | Budget | - See Appendix A | March | $29,900 |  |
|  | Funding Sponsorship Grants | - Funding Proposal to be available for distribution | December |  |  |
|  | GOLDOC | - Introduction to existing GOLDOC Sponsors | Nov-Dec |  |  |

| KRA 3: Funding |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 2. Insurance | Public Liability Volunteers | - Team Rainbow Incorporated (MOU) | December | $1.5K |  |
|  | Venue | - Existing Insurance | April |  |  |

| KRA 3: Funding |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 3. Banking | Revenue | - Team Rainbow Incorporated (MOU) | Dec-April |  |  |
|  | Expenses | - Project Manager | Jan-April |  |  |
|  | Authority | - Project Manager as per Budget/Management Committee | Ongoing |  |  |

| KRA 3: Funding |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 4. Revenue / Project Funding / Sponsorship / Grants / Crowdfunding | Funding Sponsorship Grants | - Funding Proposal | December |  |  |
|  | Crowdfunding | - Online | December |  |  |
|  | GOLDOC | - Introductions to Sponsors | Nov-Dec |  |  |

| KRA 4: Operations |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 1. Events | Media Launch | - Ambassadors at GOLDOC’s office informing the public what PHI will be - Funding Proposal released - Crowdfunding launched | December |  |  |
|  | Opening Night | - PHI opens - Invited guests | March 28 |  |  |
|  | Daily Events | - Each day highlights a designated topic ie Mental Health, Youth, Transgender, First Nation Peoples, etc. | April | $2.4K |  |

| KRA 4: Operations |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 2. Exhibitions | Australian LGBTIQ+ Sportspeople | - Curated by the Australian Lesbian & Gay Archives (Nick) - Held in Venue (Rise) | March-April | $10K |  |
|  | LGBTI People of the Commonwealth | - Existing Glasgow 2014 Exhibition to be printed & displayed - Requires updating 2014-2018 | March-April | $5K $5K |  |
|  | GOLDOC | - Support & Assistance | Ongoing |  |  |

| KRA 4: Operations |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 3. Venues | Rise | - Volunteers for Venue fit out required - Rainbow theme | March |  |  |
|  | Griffith University | - Rainbow Room for Athletes | March-April |  |  |
|  | Pop Ups | - Coolangatta - Others? | April |  |  |

| KRA 4: Operations |
| --- |
| Sub Category | Outcomes | Strategies | Timeline | Budget $ | Progress |
| 4. Volunteers | Volunteers | - Inclusiveness Training for all Volunteers provided by Queensland AIDS Council - Assume 5 Volunteers per day required - Hours of Volunteers 12pm-8pm - Polo Shirt supplied (20 x $50) - Food allowance supplied (10 days x 5 people x $20) | March April | $1K $1K $1K |  |

Future

- The Gold Coast Pride House International 2018 Business Plan aims to outline various Key Performance Areas, Outcomes, Broad Strategies and associated timelines that, it is hoped, will enable GCPHI2018 to fully engage its stakeholders and to have a planned, coordinated approach to the success of this Project.

- We realise the need for stakeholders to work together in order to bring the Project to fruition, and therefore, building partnerships is a key focus of this plan.

- For Stakeholders there are significant opportunities for successful results and ensuring appropriate legacies.

Acknowledgements:

We would like to thank the many people who provided specific and direct input into the development of this plan. We hope that each of you will now help us to make this plan the initiative that leads to the long term success of this important LGBTIQ+ Human Rights Project.

Appendix A

|  | Revenue | Expenses |
| --- | --- | --- |
| INCOME |  |  |
| Funding/Sponsorship | $ |  |
| Grants | $ |  |
| Crowdfunding | $ |  |
| TOTAL INCOME | $ |  |
| COSTS |  |  |
| Australian LGBTIQ Sportspeople Exhibition |  | $10,000 |
| LGBTI People of the Commonwealth 2014 Exhibition |  | $5,000 |
| 2014-2018 Update |  | $5,000 |
| Opening Night Entertainment |  | $3,000 |
| Daily Events 12 days x $200 |  | $2,400 |
| Public Liability & Volunteers Insurance |  | $1,500 |
| Inclusion Training |  | $1,000 |
| Uniforms |  | $1,000 |
| Volunteers Food |  | $1,000 |
| TOTAL COSTS |  | $29,900 |

# Comments

Repeat of A?